## Sheet1
Features | Estimation in Mins | Actuals | People Assigned | Planned Start Date
Mail should be sent once the password has been changed by the Ops for the (User) student or tutor | 30 |  | Swathi
Remove ID field in the Upcoming and Past session pages | 60 |  | Swathi
Display of Start and End Date in the table in all the Pages has to be formatted | 60 |  | Swathi
Change of message for the unapproved tutor login failure | 15 |  | Swathi
Add Pending session count on the Add/Deduct session Page | 20
Rename the Topic field as Session Name on the Add New Zoom Meeting Link Page | 5
Cancel button on New Zoom Meeting link should navigate back to Schedule Session Page | 10
Provide the Page heading on the Schedule Session Page | 5
Cancelling more than one session in a month should be validated. | 60
Dropdown box for Session Type on the Schedule session page should be removed and Session Type should be Paid when schedulin a Session by Ops User. Same page is used for Scheduling a Demo Page as well where Session type is Demo so ensure Session type for Demo session is always Demo | 60
Recurring checkbox need to be displayed always on Schedule Paid session Page | 15
End Time on the Scheduling session Page has to be autofilled by adding 60 mins to the Start time | 40
Display of Paused session details for the selected student(from dropdown) for the Course | 30
Formatting of Registration Student page to avoid scrolling | 40
Formatting of Availability Calendar for all Users
Freeze the table headers when scrolling down the page as need to be done on Pause Session Page
Insta Mozo
Quiz for Tutors
Demo User scheduling session for the demo Student has to display the Student Name for further communications
Providing a link on the Home Page for the Free Demo Login | 60
Page heading for the Generate Coupon Page has to be provided.
Validations for the Generate Coupon Page on lick of Save button | 40
Rename the Topic field as Session Name on the Add New Zoom Meeting Link Page
Rename the User Email on the Generate Coupon page to Student Email | 5
Allow Role Assignments tab under Site Adminsitartion > Users > Define Roles should be removed as it is mapping Roles to different roles
Change the heading of Assign roles in System page to Assign Roles to Users
Adding textbox to enter the Tutor Price for either Demo Session /Paid Session on the Tutor Cost Page for the Tutor Ops role

## Sheet2
Names | Score
Swathi | 90
Sushmita | 98
Sandhya | 99
Vaishali | 23
Prathibha | 78
Brunda | 67
Sushmita